## Template
RISK ANALYSIS TABLE for {name of the base}
!!!! Please specify the location: THE RISK ANALYSIS IS RELATED TO A SPECIFIC AREA !!!!
Last Update:
Ranking | Risk ID(1) | Vulnerabilities (2) | Contextual factors | Risks (3) | Likelihood from 1 to 5 | Impact from 1 to 5 | Reduction of Threats (Acceptance Strategy) | Reduction of Vulnerabilities (Protection Strategy) | Level of residual Risk
15 - High | Hacking (External) | Database managing all data designed by students not specialized in security. Efforts are made to make the system safe but lack of knowledge on the subject can lead to many unseen vulnerabilities. | Large community of hackers and antagonistic groups aiming to collect personal information to sell and/or use. | Data breach of user information | 2 | 5 | Compartmenatlize data to make sure that if one portion is breached, the others are not automatically also compromised. | Mitigate by employing responsible coding practices and keep security in mind when designing the system. | 10 - Medium
12 - High | Integration issues between app and website (Technical) | Lack of integrated responsiveness and adaptability | Users will be using our applications in a number of different ways (phone, tablet, computer) and we must cater to them all. | Non adaptive elements and modules leading to a worsened UX | 4 | 3 |  | Avoid through constant cross-platform and different screen size testing and using react/react native, a framework that facilitates code reuse | 6 - Low
12 - High | Requirements and user stories backlog mismanagement | Requirements are defined by a list of "wants" and further questions to the contractor may be understood incorrectly | Requirements are defined directly through a list, but still leave room for interpretation of implementation | Possibility of missing requirements, as well as a bad priority system of requirements | 3 | 5 |  | Mitigate by the use of backlog grooming sessions to keep the backlog updated and prioritized | 4 - Low
12 - High | Unfamiliarity with the tech stack for front-end and back-end integration (Technical) | The teams unfamiliarity with the tech stack used can lead to integration difficulties | As our team is new to large scale development like this project, very few of us are familiar with the frameworks we have decided to use. | Consequence is a higher proportion of bugs and issues in the finished product, as well as a slower development time | 5 | 2.5 |  | Mitigation through training sessions for team members on the elements that are lesser known technologies, utilize team members strength and previous experiences, frequent meetings so there is coherence between front and back team, so collaboration is seamless. | 9 - Medium
10 - Medium | Insufficient documentation (Technical) | Bad documentation for the system architecture can lead to data redundancy, lack of understanding and inconsistent updates when implementing the database | The team cannot be meeting about every small matter and thus need some ideas and decisions made ahead of time. | Consequence is lower overall code quality and poor understanding by new programmers on the project | 2 | 5 |  | Avoid by working on the domain model early on and ensuring collaboration between the development team and the team members working on the system architecture | 8 - Medium
10 - Medium | Neglecting core features or requirements (Technical) | Bad prioritization and/or communication in the team can lead to this |  | Consequence is not meeting client/contractual expectations | 1 | 5 |  | Avoid by generating extensive user stories and thorough dissection of client needs. | 6 - Low
10 - Medium | Non-adherence to UI/UX standards (Technical) | Failure to meet user interface design norms creates issues |  | Consequence is deprecating the user experience | 2 | 4 |  | Mitigation by following UI/UX best practices , user testing. | 5 - Low
10 - Medium | Design pattern misuse (Technical) | Incorrect application of design patterns can overcomplicate a system and creating issues |  | Consequence is a worsened user experience | 2 | 4 |  | Mitigation by conduction design review sessions | 5 - Low
9 - Medium | Lack of stakeholder engagement (Management) | A large team, as well as many stakeholders can be hard to manage and keep track of | Getting quality feedback and useful comments from stakeholders can be difficult if they are not effective communicators. | Consequence is a disconnect between stakeholder wants and developer assumptions | 3 | 3 | Following good coding practices to make backtracking easier if any issues come up with expectations | Mitigation by regular update meetings, stakeholder management strategies. | 9 - Medium
9 - Medium | Inconsistent data handling for different user types (Technical) | There are many different types of users with different requirements and views of the platform, this could result in inconsistencies and potential data errors |  | Data errors, and thus bugs | 1 | 3 |  | Avoidance through making sure that the data handling protocols are clear and data validation checks are made through the development process | 8 - Medium
9 - Medium | Not meeting deadlines (Management) | Hard deadlines may be missed, disappointing the client and disrupting the overall development timeline | The devellopers of this project are students, and as such have many other responsibilities and projects to keep track of. | Consequence is disappointing the client, as well as breaching contractual obligations. | 2 | 3 |  | Mitigate by creating internal “soft” deadlines to be respected by the team, as well as encouraging | 6 - Low
9 - Medium | Insufficient user testing (Technical) | As the project grows in size, the amount of possible sources of bugs and issues increase. |  | Consequence is bugs and usability issues are discovered by users, impacting their experience negatively | 3 | 2 | It is an impractical goal to want to ensure with certainty that there are no bugs in the system. Our time and resources being limited, we will not be able to cover all bases. We still need to ensure an adequate amount of testing. We aim for 80% coverage. | Testing and code reviews can be used to locate bugs and issues ahead of time. | 4 - Low
6 - Low | Unavailability of team members (Management) | Some members are the main contributors to specific parts of the project such as one person focused on testing for example | As students, schedules are pretty packed with work, studying, or friends. Emergencies or unforseen circumstances are also possible | Consequence is slowing development due to dependency on certain members | 2 | 3 |  | Cross-training team members to be able to perform a variety of tasks and outsourcing tasks when necessary | 5 - Low
6 - Low | Conducting regular scrum meetings (Schedule) |  | As students, schedules are pretty packed with work, studying, or friends. This leads to difficulty maintaining regular meetings with the entire team | Consequence is a lack of team cohesion and confusion among members | 1 | 3 | It is not feasible to expect every member to be at every meeting and thus, meeting minutes are kept to keep everyone up to date and aware of meeting material/decisions | Mitigation by holding virtual meetings, utilizing when to meet, making meeting minutes so team members can stay updated and establishing clear meeting times to maximize attendance. | 4 - Low
5 - Low | Misaligned code management practices (Technical) | Inconsistent use of version control and coding workflows. |  | Consequence is lower overall code quality and poor understanding by new programmers on the project | 1 | 2 |  | Mitigation by mandatory code review policies in the group. | 3 - Very low
5 - Low | Ressource availability (Management) | Potential shortfall in tools and programmers. | As students, both time and money are important factors to consider. Any services used will most likely be free, and thus more limited. | Consequence is starvation for important tasks | 1 | 3 |  | Mitigation by resource planning, cross-training and contingency reserves. | 2 - Very low
4 - Low | Limited budget for tooling (Budget) | The use of cheaper, or free tools can be alluring but may not be the best quality, and thus the most secure. |  | Consequence is having limited options for hosting and/or tools | 1 | 2 |  | Mitigate by using free trials and free versions of tools. Some companies offer free premium versions for students | 3 - Very low
3 - Very low | Disorganized teams leading to double work (Management) | Multiple teams/members may work on the same features or systems and overwrite each other’s contributions. As well as waste time in the process. |  | Consequence is time lost and possible conflict to decide which version is “better” | 1 | 2 | If this happens, code review by the two people who double worked can be done to determine pros/cons of both implementations. The final result took more time to complete, but is ultimately better | Mitigate by having team leaders communicating frequently, a Github repository so all members are aware of current work, and task management software such as Trello to organize tasks. | 3 - Very low
3 - Very low | Dependence on external APIs (Technical) | Dependencies on external APIs for certain features may introduce risks, including changes in API specifications or unexpected downtime. | External APIs can be invaluable tools for accelerating work and acheiving things it would be unreasonable to complete within a 3 month time frame. | Consequence is security risks and dependency on API changes | 1 | 3 | We must accept these risks as we have no control on external software and have no contact with API providers | Mitigate by using few APIs and coding most features and components ourselves to best control our code. | 2 - Very low

## Example
RISK ANALYSIS TABLE for BASE
Last Update:
Ranking | Threats (1) | Vulnerabilities (2) | Contextual factors | Risks (3) | Likelihood from 1 to 5 | Impact from 1 to 5 | Reduction of Threats (Acceptance Strategy) | Reduction of Vulnerabilities (Protection Strategy) | Level of residual Risk
9 - Medium | Transport accidents (Indirect threat) | Fleet: - Large fleet (vehicle and motorbikes) - Bad state : 50% of cars are in bad state - 30% of motorbike are in bad state - high number of daily movements with a lack of coordination RH - Lack of leadership of direct line managers of drivers - No regular team meetings and refreshing trainings - no respect of drivers' and passengers' regulations Communication - No follow up of movements of vehicles and motorbikes - No strategy of communication equipment (movements) - no global covering (phone and radio) | State of roads enhance speed on highways with unappropriate equipment, uneven on secondary roads, animals Driving (in general) - Bad state of national fleet, especially public transports. - Poor respect of raods regulation - wet season and dark hours are more risky | To be subjected to a transport accident | 3 | 3 |  | • System of regular control (respect of rules and regulation) to be implemented • Review and update of SOP • Implement communication strategy, rules and system between vehicles and bases • Plan of renewing vehicles • Improve the planning of movement (reduce number of movement and reduce speed) • Maximal driving distances, obligation for drivers to take a break • Plan coaching of direct line managers and trainings session for drivers and bikers •Plan regular team meetings/workshop •Officialize adherence to rules by drivers and passengers (Review of vehicle policy, sensitization, trainings and signing by every one) • implement a strict adherence to use of safety clothing and equipments • plan regular Safety refreshing trainings (drivers and programs) | 6 - Low
8 - Medium | EID / RCIED / Anti tank mines (Indirect threat) | . Movement to our intervention area . Mistaken identity | Report major incidents: . Suspected IED discovered on XXX main road on 11th November . Few incident have been occurred on the road between XX . One RCED attack against demining organization on 2010 . One RCED on the road from XXX . 2 RCED attack in XXX in 2009. on 2010 one more on the road from XXX | To be subjected to an EID/RCIED/Anti tak mine explosion | 2 | 4 | . Community support & contact with AOG | . Limitation of movement . Collection of information from locals before using the road (constant re-assessment of the situation) . Not to be the 1st car to take the road . Use of alternative roads . Use of low profile cars . Movement with public transportation | 5 - Low
8 - Medium | Suicide attack (Indirect threat) | . Wrong time in wrong place related to: . convoys . Governmental, UN, embassies buildings | . The most recent suicide attacks was in xx, the target was XXX convoy district in XX area . Attack on XXX in district XXX in July. . In 2009: complex attacks to XXX . Most of suicide attacks are occurring in the morning before 9AM. | To be subjected to a suicide attack | 2 | 4 |  | . Avoid going to Governmental offices before 9am. Official meetings after 9:30am . UN guest houses, GH and offices located close to GOA and UN buildings and embassies are no go areas. . Restricted list of recreative locations. . Distance from military convoys . Avoid traffic congestions. . Low profile policy Refer to the current SOPs | 4 - Low
8 - Medium | Kidnapping (Crime related) | . Presence of 8 International staff in KBL . Movements during and out of working hours | . Strong presence of Afghan security personnel in the city . No kidnapping of NGO international staff reported in 2009/2010 . 2008: NGO staff kidnapped in district 5 CH Qambar + kidnapping AFRAN in Karte Parwan. | To have an international staff victim of a kidnapping or an hostage taking | 2 | 4 | low profile policy | . Confidentiality & unpredictability of movement, . No use of HF and VHF . Group movement & presence of a guard in addition of a driver for any movement . Walking restriction. . Mapping: no go areas clearly identified. . Low profile policy Refer to the current SOPs | 4 - Low
6 - Low | Crowd/mob/riot (Indirect threat) | . Wrong time, wrong place during movements. . Population perception of NGO | . In 2010, violent demonstration in district X and 5 between XX and XX. . Demonstration of election candidate followers due to result of election. . 2010: media reports that NGOs are involved in convertion to chrystianity. . NGO perception fluctuant | To be subjected to a crowd / mob/riot | 2 | 3 | . Low profile policy . To respect the culture of the people in terms of religion and living. | . Good information collection and adapted movement plan . Communication with teams during movement: alert system . Only HoM in contact with media . No sign and logo to the office and GH Refer to the current SOPs | 3 - Very low
2 - Very low | Armed Robbery (Crime related) | . Perception of expatriates & international organizations . Cash movement | . Criminality is assessed as being low for the time being | To be victim of a robbery | 2 | 1 | . low profile policy . good relations with neighbours in case of evacuation from ACF premises | . 2 guards per shift, . Existing & implemented cash policy Refer to the current SOPs and national security plan | 2 - Very low
CONFIDENTIAL